## POA&M Tracker
PLAN OF ACTION & MILESTONES (POA&M) — Healthcare Security Assessment
Prepared by: Tamia Williams ¦ Assessment Date: May 2025 ¦ Status: Active Remediation
POA&M ID | Finding ID | Control ID | Weakness Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Remediation Action | Responsible Owner | Resources Required | Scheduled Completion | Actual Completion | Status | % Complete | Notes / Evidence
POA-001 | F-001 | AC-6 | Users granted excessive system access beyond job function requirements. | 4 | 5 | 20 | CRITICAL | Implement RBAC framework; deploy centralized IAM; enforce quarterly access audits. | IT Security Officer | IAM platform license; 40 hrs IT labor | 2025-09-30 |  | Open | 0 | NIST SP 800-53 AC-6; User access review 05/2025
POA-002 | F-006 | IA-2 | Remote and privileged access lacks MFA enforcement, exposing PII. | 4 | 5 | 20 | CRITICAL | Enforce MFA for all remote and privileged accounts per NIST SP 800-63. | IT Security Officer | MFA solution license; 20 hrs implementation | 2025-09-30 |  | Open | 0 | Authentication config review 05/2025; NIST SP 800-63
POA-003 | F-003 | RA-3 | No current organizational risk assessment exists. | 3 | 5 | 15 | HIGH | Conduct full NIST SP 800-30 risk assessment; schedule annual reassessments. | CISO | External assessor or 60 hrs internal labor | 2025-09-30 |  | Open | 0 | Document request 05/2025; SSP review
POA-004 | F-002 | CA-7 | No SIEM or automated monitoring in place; detection is manual. | 4 | 4 | 16 | HIGH | Deploy SIEM with automated alerting, baselines, and 24/7 coverage. | SOC Lead | SIEM license; 80 hrs config + integration | 2025-12-31 |  | Open | 0 | Network architecture review 05/2025; NIST SP 800-137
POA-005 | F-007 | SI-3 | Multiple workstations running unlicensed or no antivirus software. | 3 | 4 | 12 | HIGH | Deploy enterprise-grade EDR; centralized mgmt and auto-updates. | Endpoint Security Mgr | EDR license; 16 hrs deployment | 2025-09-30 |  | Open | 0 | Endpoint inventory scan 05/2025; software license audit
POA-006 | F-004 | CA-5 | No structured POA&M tracking process exists for known vulnerabilities. | 3 | 3 | 9 | MODERATE | Establish POA&M process within GRC platform with ownership and deadlines. | Compliance Manager | GRC platform (or spreadsheet); 16 hrs setup | 2025-09-30 |  | Open | 0 | GRC platform audit 05/2025; prior audit findings
POA-007 | F-005 | RA-7 | Risk acceptance decisions are undocumented and inconsistently applied. | 3 | 3 | 9 | MODERATE | Establish cross-functional risk committee; document all risk decisions. | Compliance Manager | 4 hrs/quarter committee meetings | 2025-12-31 |  | Open | 0 | Stakeholder interviews 05/2025; incident log review

## Risk Matrix
RISK SCORING MATRIX — Score = Likelihood × Impact
| Impact 1 Negligible | Impact 2 Minor | Impact 3 Moderate | Impact 4 Major | Impact 5 Critical
5 — Almost Certain | 5 | 10 | 15 | 20 | 25
4 — Likely | 4 | 8 | 12 | 16 | 20
3 — Possible | 3 | 6 | 9 | 12 | 15
2 — Unlikely | 2 | 4 | 6 | 8 | 10
1 — Rare | 1 | 2 | 3 | 4 | 5
LOW (1–5)
MODERATE (6–11)
HIGH (12–19)
CRITICAL (20–25)

## Control Reference
NIST SP 800-53 Rev. 5 — Control Reference
Control ID | Control Name | Control Family | Assessment Result | Risk Score | Remediation Status
AC-6 | Least Privilege | Access Control | Other Than Satisfied | 20 | Open
CA-5 | Plan of Action and Milestones | Assessment & Authorization | Other Than Satisfied | 9 | Open
CA-7 | Continuous Monitoring | Assessment & Authorization | Other Than Satisfied | 16 | Open
IA-2 | Identification & Authentication | Identification & Auth | Other Than Satisfied | 20 | Open
RA-3 | Risk Assessment | Risk Assessment | Other Than Satisfied | 15 | Open
RA-7 | Risk Response | Risk Assessment | Other Than Satisfied | 9 | Open
SI-3 | Malicious Code Protection | System & Info Integrity | Other Than Satisfied | 12 | Open

## Dashboard
POA&M DASHBOARD — At a Glance
Total Findings | Open | In Progress | Closed | High / Critical | Moderate | Low | Target: Q3 2025
7 | 7 | 0 | 0 | 3 | 2 | 2 | 5
POA&M ID | Control | Finding | Risk Score | Risk Level | Owner | Target | Status
POA-001 | AC-6 | Least Privilege Not Enforced | 20 | CRITICAL | IT Security Officer | Q3 2025 | Open
POA-002 | IA-2 | No MFA Enforcement | 20 | CRITICAL | IT Security Officer | Q3 2025 | Open
POA-003 | RA-3 | Risk Assessment Outdated / Missing | 15 | HIGH | CISO | Q3 2025 | Open
POA-004 | CA-7 | No Continuous Monitoring / SIEM | 16 | HIGH | SOC Lead | Q4 2025 | Open
POA-005 | SI-3 | Inadequate Endpoint Protection | 12 | HIGH | Endpoint Sec Mgr | Q3 2025 | Open
POA-006 | CA-5 | No Formal POA&M Process | 9 | MODERATE | Compliance Mgr | Q3 2025 | Open
POA-007 | RA-7 | Inconsistent Risk Response Decisions | 9 | MODERATE | Compliance Mgr | Q4 2025 | Open